# AI Character Creator — Client Response

Proposed MVP • R.Royale and Summer Breeze • Two short answer lines per question

## 1. What would the first prototype deliver?

A small creator interface, two reusable characters, and one approximately 60-second, 1080p conversation.

Both women share one seated scene; V1 produces an offline video with visible listener reactions.

## 2. How would the characters differ?

R.Royale starts calm, dry and controlled; Summer Breeze starts louder, animated and expressive.

Each has a distinct approved voice and appearance, with editable personality and delivery settings.

## 3. How would regional speech and AAVE work?

Separate regional vocabulary, AAVE features, slang, pronunciation, cadence and code-switching from identity.

V1 offers a few creator-approved presets and line overrides; African-American identity never selects a dialect.

## 4. Can creators write the exact dialogue?

Yes: scripted mode locks the words and applies saved voice and performance settings without rewriting.

Generated mode creates an editable draft; creators approve it before speech and video generation.

## 5. Which LLM would you use?

OpenAI GPT-4.1 mini would draft structured dialogue and performance cues through a Python service. [OpenAI model]

One scene planner maintains both personalities and continuity; a separate agent per character is unnecessary.

## 6. Which voice technology would you test?

ElevenLabs Eleven v3 is the first choice; Cartesia Sonic 3 is the comparison candidate. [ElevenLabs controls] [Cartesia SDK]

Audition two licensed or designed voices; expressive control and regional pronunciation require listening tests.

## 7. Which avatar/video technology would you use?

Use two original MetaHuman characters rendered together in Unreal Engine, with persistent faces and bodies.

Test HeyGen Avatar IV for a visual benchmark; its documented workflow does not establish our shared-scene needs. [HeyGen guide]

## 8. Which lip-sync, facial and body technology would you use?

Use MetaHuman Animator for audio-driven facial movement; test NVIDIA Audio2Face-3D as an alternative. [MetaHuman animation] [NVIDIA animation]

Use Unreal Sequencer, Control Rig and licensed gesture clips for body motion, eye contact and listener reactions.

## 9. How would both characters react naturally?

A shared timeline drives separate speech, facial, gaze and body tracks while both characters remain visible.

Schedule nods, smiles, breathing and restrained reactions around the dialogue; manually polish the final performance.

## 10. What would you build versus integrate?

Build the editor, saved profiles, dialogue modes, scene planning, provider adapters, job tracking and export flow.

Integrate existing LLM, TTS, facial-animation and rendering tools; no custom foundation-model training is needed.

## 11. How would character settings be saved and reused?

Version profiles in a database: personality, vocabulary, pronunciation, cadence, voice mapping and gesture settings.

Store face/body assets, hair, clothing, rigs, approved audio, scene files and consent records in asset storage.

## 12. How would you avoid provider dependency?

Keep dialogue, audio, animation and rendering behind separate interfaces with owned profiles and standard exports.

Replacement remains possible, but matching a proprietary voice or retargeting a rig will require new validation.

## 13. What are the consent safeguards?

V1 uses original fictional designs and licensed or designed voices, with recorded provenance and AI disclosure.

Real-person uploads stay disabled until verified authorization, permitted-use records and revocation controls exist.

## 14. What is the estimated V1 timeline and development cost?

Budget 6–8 weeks and 200–280 hours; at an illustrative $50/hour, development is $10,000–$14,000 USD.

This planning estimate includes basic character setup and two review rounds; bespoke art and delayed approvals add scope.

## 15. What are the expected third-party costs?

Allow approximately $1–$7 per final-minute render attempt, plus $200–$500 for prototype testing and hosting.

Reserve $300–$1,000 separately for licensed assets; subscription minimums and any required engine seats are extra.

## 16. What relevant experience can be claimed?

No verified portfolio was supplied, so this proposal makes no claim of previously shipped avatar projects.

Before sending, add genuine project links and your exact contribution; present third-party animation work transparently.

## Official references — checked 21 September 2026

OpenAI model: https://developers.openai.com/api/docs/models/gpt-4.1-mini

ElevenLabs controls: https://elevenlabs.io/docs/overview/capabilities/text-to-speech/best-practices

Cartesia SDK: https://github.com/cartesia-ai/cartesia-python/blob/main/examples/examples.py

HeyGen guide: https://help.heygen.com/en/articles/11269603-heygen-avatar-iv-complete-guide

MetaHuman animation: https://dev.epicgames.com/documentation/metahuman/audio-driven-animation

NVIDIA animation: https://docs.nvidia.com/nim/digital-human/a2f-3d/latest/